## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a data engineer, I want to collect and preprocess transaction data so that it can be used for model training. | Must Have | Dataset availability | Backend Team | Completed
Sprint 2 | Sprint 2 | US002 | As a data scientist, I want to train an ML model that predicts fraudulent transactions using historical data. | Must Have | Cleaned data | Backend Team | Completed
Sprint 3 | Sprint 3 | US003 | As an AI developer, I want to integrate an LLM to provide human-readable explanations for fraud predictions. | Should Have | Trained model | Backend Team | Completed
Sprint 4 | Sprint 4 | US004 | As a frontend developer, I want to create an interactive dashboard that displays transaction risk results and performance metrics. | Must Have | APIs ready | Frontend Team | Completed
Sprint 4 | Sprint 4 | US005 | As a DevOps engineer, I want to deploy and integrate the entire system in a test environment for demonstration. | Could Have | Backend & frontend integration | Both Teams | Completed
Note on F1: Sumeet Kumar Barua08: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US001 | T1 | Collect transaction dataset and verify structure | 2025-09-10 | 2025-09-11 | Tejashvar K.R,Abhishek | Data Collection | Done | 6 | bar: Day 1 to Day 2
US001 | T2 | Clean missing values and normalize features | 2025-09-12 | 2025-09-14 | Tejashvar K.R,Abhishek | Data Cleaning | Done | 10 | bar: Day 2 to Day 4
US002 | T3 | Train ML model (Random Forest) for fraud prediction | 2025-09-15 | 2025-09-18 | Tejashvar K.R,Sampreeth | Model Training | Done | 12 | bar: Day 3 to Day 6
US003 | T4 | Integrate LLM to generate prediction explanations | 2025-09-19 | 2025-09-21 | Ravi Teja | AI Integration | Done | 8 | bar: Day 4 to Day 6
US004 | T5 | Create frontend dashboard for fraud prediction visualization | 2025-09-22 | 2025-09-25 | Sampreeth ,Tejashvar,Ravi Teja,Aman | UI Development | Done | 10 | bar: Day 5 to Day 8
US005 | T6 | Deploy backend and frontend to test environment | 2025-09-26 | 2025-09-28 | Sampreeth ,Tejashvar,Ravi Teja,Aman | Deployment | Done | 8 | bar: Day 6 to Day 9
Note on I2: Sumeet Kumar Barua08: This is the total task estimated in hours for all the user stories
Note on J2: Sumeet Kumar Barua08: Pending effort hours after completion of day 1 work
Note on K2: Sumeet Kumar Barua08: Pending effort hours after completion of day 2 work
Note on L2: Sumeet Kumar Barua08: Pending effort hours after completion of day 3 work
Note on M2: Sumeet Kumar Barua08: Pending effort hours after completion of day 4 work
Note on N2: Sumeet Kumar Barua08: Pending effort hours after completion of day 5 work
Note on O2: Sumeet Kumar Barua08: Pending effort hours after completion of day 6 work
Note on P2: Sumeet Kumar Barua08: Pending effort hours after completion of day 7 work
Note on Q2: Sumeet Kumar Barua08: Pending effort hours after completion of day 8 work
Note on R2: Sumeet Kumar Barua08: Pending effort hours after completion of day 9 work
Note on S2: Sumeet Kumar Barua08: Pending effort hours after completion of day 10 work
Note on T2: Sumeet Kumar Barua08: Pending effort hours after completion of day 11 work
Note on U2: Sumeet Kumar Barua08: Pending effort hours after completion of day 12 work
Note on V2: Sumeet Kumar Barua08: Pending effort hours after completion of day 13 work
Note on W2: Sumeet Kumar Barua08: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 2 | Day 3 | ML model taking too long to train due to large dataset | Reduced features and applied stratified sampling
Sprint 2 | Day 4 | API returning 500 error during prediction | Debugged endpoint, fixed missing JSON key
Sprint 3 | Day 2 | LLM responses too long and inconsistent | Applied temperature control and prompt optimization
Sprint 4 | Day 1 | Frontend not fetching data due to CORS issue | Enabled CORS in Flask backend

## Retrospection
Sl No | Sprint # | Sprint start date | Sprint end date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-09-10 | 2025-09-14 | Tejashvar K.R | Document preprocessing steps clearly | Rushing into training without validation | Collaborating during data cleaning | Created shared preprocessing document
2 | 2 | 2025-09-15 | 2025-09-21 | Ravi Teja | Use version control for model files | Using large data without sampling | Testing each version before training | Implemented model versioning
3 | 3 | 2025-09-22 | 2025-09-25 | Sampreeth, Aman | Write prompts clearly for LLM | Using unstructured prompts | Evaluating prompt output for accuracy | Finalized best-performing prompts
4 | 4 | 2025-09-26 | 2025-09-30 | Tejashvar K.R | Prepare documentation parallelly | Waiting till the end to test integration | Regular cross-team syncs | Weekly integration meetings scheduled

## Defect Log
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | Backend_Team | 2025-09-16 | API returned 500 error when no transaction ID was provided | Sprint 2 | Tejashvar K.R,Ravi Teja | Functional | Added input validation to check for empty transaction ID before model call | 2025-09-17 | Closed | Handled using try-except and input schema validation
2 | Frontend_Team | 2025-09-18 | Dashboard graph not updating after prediction result | Sprint 2 | Sampreeth,Aman | UI/Integration | Added state refresh in React after API call completion | 2025-09-19 | Closed | Graph now updates dynamically post prediction
3 | Backend_Team | 2025-09-20 | Model predictions inconsistent after multiple API calls | Sprint 2 | Tejashvar K.R | Logic | Fixed model reloading issue by loading model once globally | 2025-09-21 | Closed | Improved model loading logic for better performance
4 | Frontend_Team | 2025-09-24 | Frontend CORS error while calling backend API | Sprint 3 | Aman | Integration | Enabled CORS headers in Flask backend using flask-cors | 2025-09-25 | Closed | Frontend and backend communication successful
5 | Backend_Team | 2025-09-26 | LLM returning incomplete explanation in fraud reasoning | Sprint 3 | Ravi Teja | AI/LLM | Adjusted prompt structure and reduced temperature to improve clarity | 2025-09-27 | Closed | LLM responses more consistent now
6 | Frontend_Team | 2025-09-28 | Prediction table incorrectly showing confidence score | Sprint 3 | Sampreeth | UI/Functional | Fixed JSON key mapping in frontend API response | 2025-09-29 | Closed | Confidence score now displays correctly
7 | Testing_Team | 2025-09-29 | Dashboard loading time too high when fetching data | Sprint 4 | Both Teams | Performance | Added backend pagination & frontend lazy loading | 2025-09-30 | Closed | Dashboard now loads efficiently
8 | Frontend_Team | 2025-10-01 | Model performance metrics table not showing updated values | Sprint 4 | Frontend_Team | UI/Data Sync | Triggered metric fetch API after every model retrain | 2025-10-02 | Closed | Metrics table updates automatically
9 | QA_Team | 2025-10-03 | Fraud/Legit chart overlapping on mobile view | Sprint 4 | Frontend_Team | UI/Responsive | Fixed responsive layout using CSS grid and media queries | 2025-10-04 | Closed | Dashboard mobile-friendly now
10 | Backend_Team | 2025-10-04 | Deployment failed on Render due to missing environment variables | Sprint 4 | Backend_Team | Deployment | Configured .env variables and updated deployment script | 2025-10-05 | Closed | Successfully deployed backend service